# Action plan 2016 – 2017

**Name of Professional Unit: Section Libraries for Children and Young Adults**

**Objectives of Professional Unit/Strategic Programme Committee 2017
Written by Ingrid Bon (Chair until Jan 2017)
Updates written by Ulla Pötsönen (Interim Chair from Jan 2017)**

1. *Increase the level of discussion among Section’s Members (and future Section’s members) in order to develop out network. This will help us to achieve contributions to Key Initiatives in future.*
2. *Contribute to the development of advocacy materials to support libraries’ roles in the Sustainable Development Goals by supplying Section -related content and promoting discussion among Members (Key Initiative 4.1 Promoting libraries within the United Nations 2030 Agenda for Sustainable Development* [*http://www.ifla.org/node/10091*](http://www.ifla.org/node/10091)*)*
3. *Develop and spread section standards e.g.: Guidelines, World through picture Books.*
4. *Inform library society on specific topics regarding Library services for children and/or young adults via Facebook, Newsletter, Twitter, sessions at WLIC etc.*
5. *Keep focus on the importance of Literacy and Reading in cooperation with other sections as LiR, Public Libraries and School Libraries*

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives*What do you want to achieve? Use your list above* | Project or activity*What project or activity are you going to do?* | Main tasks*What are the specific things you need to do?* | Responsibilities and timeline*Who will do them and by when?* | Resources*Do you need specific skills, money or technology?* | Communications*How will you communicate your achievements? To whom? By when?* | Measures of success*How will you show the impact of your work?* | Progress*Report here briefly the progress of your work, at least every month* |
|  |  |  |  |  |  |  |  |
| 1.World through Picture books  | Small project in order to change into web based document instead of printed version | 1.doc on webpages to fill for newcomers2. web based doc that can be updated easy | Ingrid Bon: permission from illustrator to use design. Oral agreement is there, written will follow in January 2017.Annie Everall:Manual for new contributionsSwitch present countries into web based document, July 2017 | YesRequest for new project | Information coordinator via newsletter, FacebookAll members via Twitter | Every year 5 new countries participating | 3/17:Project postponed to 2018 as the schedule is too tight. It is not a “small project”! Re-applying the funds in October.Discussion and forming a working group in Wroclaw. Askingstudents or interested ppl for the work.No written agreement from designer. |
| 2. Revision of Guidelines Library Services for children | Final part of the project | Imput gathered via sections, workshop Oslo and WLIC 2016 to be put into a document.Concept to be discussed in MidYear meeting Gothenburg march 2017 | Section Ch/YACarolyn Rankin +Working groupChair/secretary | YesRemaining project money | Mid Year meeting Gothenburg in March 2017, (Ingrid Kallstrom), Newsletter (Ulla Potsonen), mail to section members (Ingrid Bon) | Professional Report publication | 3/17: The draft was discussed in Gothenburg. Work in Basecamp continues.Session in Wroclaw.Mail to Section members after Wroclaw. |
| 3. Collect and publish Best Practices in Library Services for Children | Active call for participationSpecial workshop for Polish librarians day before WLIC 2017 | Communication plan | Working groupChair/secretary | YesRemaining project money | Based on communication plan others beside section will be informed |  | 3/17: SC members promoting the project during the spring. Workshop day will be an evening in Wroclaw (see session planning) |
| 4. Sister Libraries | Ongoing activity |  |  |  |  |  | 3/17:short review in midterm meeting |
| 5.Plan sessions for Wroclaw, WLIC 2017 | 2 sessions1 on Revision Guidelines project1 together with LiR , Public Libraries, School Libraries | Work on:Call for papers, review papers, business as usual for congress | Standing committee members who volunteeredChair/secretary | Maybe admin funds | SC members will be informed | email | 3/17: 2 Session planning work going on,plus planning an open evening for local librarians about Guidelines connecting to Best Practices |
| 6. ALMA | Yearly nomination process |  | SC and paperwork done by secretary Ingrid Kallstrom |  |  |  | 3/17Nominations from previous year renominated, a working group in Wroclaw to the issue (seeking candidates year round) |
| 7. Vision meeting Athens april 2017  |  |  | Ingrid KallstromIngrid BonBoth will attend this special session |  |  |  | 3/17 Instead of Ingrid Bon, Ulla Pötsönen |